## Project Priorities
Score and Rate Potential Projects
|  | Planning Period: | Fiscal Year 2008
Step 1 - List each of the potential projects under consideration by the Review Board
Milestone 0 Review Done?
Project Name |  |  |  | Sponsor |  |  | Additional Comments
1. Compliant Earned Value Management System |  |  |  | PMO |  | Yes | Mandated project and already in progress
2. Cost Estimation and Budgeting for IT Projects |  |  |  | Office of Finance |  | No | Very complex and long project to implement
3. Performance Management System for Operational Projects |  |  |  | Office of the CIO |  | No | Somewhat difficult to implement
4. Cost Data Integrity / Performance Reporting |  |  |  | Office of the CIO + PMO |  | No | Relatively easy project with quick turnaround
5. Enterprise Risk Management Program |  |  |  | PMO |  | No | Fairly easy project to complete
Step 2 - Score and Rate each of the above projects on a scale between 1 to 5 (1 = lowest / 5 = highest)
2.1 | Who performed the evaluation summarized below? |  |  | Office of Information & Technology Review Board
2.2 | When was this evaluation done? |  |  | 2006-11-16
|  |  |  | Degree of Strategic Alignment | Likeliness of Project Success |  | Close to the Customer | Low Cost to Implement | Critical to Business Processes | Definite Impact to the Bottom Line
Project as listed above
1. Compliant Earned Value Management System |  |  |  | 3 | 2 |  | 2 | 4 | 3 | 1
2. Cost Estimation and Budgeting for IT Projects |  |  |  | 1 | 4 |  | 1 | 3 | 4 | 1
3. Performance Management System for Operational Projects |  |  |  | 4 | 3 |  | 1 | 3 | 3 | 1
4. Cost Data Integrity / Performance Reporting |  |  |  | 3 | 5 |  | 2 | 5 | 4 | 1
5. Enterprise Risk Management Program |  |  |  | 2 | 3 |  | 3 | 4 | 2 | 3
Step 3 - Summarize the Scores
1. Compliant Earned Value Management System |  |  |  | 15
2. Cost Estimation and Budgeting for IT Projects |  |  |  | 14
3. Performance Management System for Operational Projects |  |  |  | 15
4. Cost Data Integrity / Performance Reporting |  |  |  | 20
5. Enterprise Risk Management Program |  |  |  | 17
0
0
0
0
0
0
0
Step 4 - Display the Results as a Pareto Chart (use the Macro's below to get started)
NOTE: Before doing the Pareto Chart, Step 3 data should be sorted in descending order.
1. You can hit the Control Shift S keys to run a simple macro to do the sort.
2. Once the data has been sorted, hit the Control Shift P keys to generate a simple pareto chart.
Note on J6: Indicate if the project has completed the Conceptual Milestone 0 Review and is ready to move to Milestone 1 - Project Initiation.
Note on G7: Indicate if the project has a sponsor. If multiple sponsors, then indicate the highest organizational level that is sponsoring the project.
Note on G26: How well does this project align and impact the strategies of the organization, such as goals and objectives as well as departmental performance goals.
Note on I26: Does this project appear likely to meet its overall purpose. This can depend upon things like complexity of the project, can it secure the right people and funding, etc.
Note on M26: Relative to other projects, this project is not very costly to fund and implement over the entire life cycle of the project.
Note on K26: This project will touch our customers and improve our services and satisfaction to the customer
Note on O26: This project addresses or impacts a critical business process in a very positive way; such as fixing a broken process that is mission critical to the business.
Note on Q26: This project has a measurable impact on reducing our costs and/or improving our income; and thus it will impact the bottom line.