Project Closeout Report

Cost Data Integrity Project

| VERSION: 1.0 | REVISION DATE: February 22, 2008 |
| --- | --- |

Approval of the Project Closeout Report indicates an understanding that this project is now considered closed by the Project Team, its sponsors and the IT Governance Council within the Office of Information and Technology.

| Approver Name | Title | Signature | Date |
| --- | --- | --- | --- |
| Matt H. Evans | Project Manager |  |  |
| Marshall Burley | Director, Program Management Office |  |  |
| William F. Supple | IT Process Board |  |  |

# Section 1.	General Information

| Project Name | Date |
| --- | --- |
| Cost Data Integrity | February 22, 2008 |
| Organizational Unit |
| Program Management Office – Office of Information and Technology |
| Project Manager | Phone | Email | Fax |
| Matt H. Evans | 877-807-8756 | matt@exinfm.com |  |

Section 2.	Goals / Objectives / Expectations of Project

Describe specific goals and objectives of this project. For each, indicate if the project was successful in meeting the goal or objective.

| Item | Project Goal or Objective | Met? |
| --- | --- | --- |
| 2.1 | Reduce the error rates associated with timesheet submissions which in turn is distorting actual costs reported in the Project Management System. | Yes No |
| 2.2 | Reduce the error rates associated with vendor invoices which in turn is distorting actual costs reported in the Project Management System. | Yes No |

Section 3.	Project Risks and Issues

Indicate if any risk per the Risk Management Plan occurred and turned into an issue. Describe how the issue was resolved or indicate if the issue is still open.

| Item | Risk per Project Plan | Open Issue |
| --- | --- | --- |
| 3.1 | Scope Creep – Requirements may change during the course of the project, such as System Requirements for PMS. Final Disposition > Never occurred, high level functional requirements were described and turned over to the PMO to pursue. | Yes No |
| 3.2 | Access to PMS and FMS Records – In order for this project to be successful, it was critical to have quick access to both PMS data and FMS data. Final Disposition > Thanks to high level sponsorship of this project, these obstacles never occurred. System Administrators were more than helpful in providing all of the data requests submitted by the project team. | Yes No |
| 3.3 | Team Resources – There was an initial concern that project staff would not be available to take on all of the tasks associated with this project. Final Disposition > This never materialized despite the fact that the staff was pulled off the project several times. The Project Manager was able to meet the project schedule primarily due to the straight forward solutions needed to re-engineer the processes. | Yes No |
| 3.4 | Bad Data – There was a risk that the data that was received from both PMS and FMS would contain errors. Final Disposition > There were inconsistencies in how the data was entered; especially invoice numbers. However, overall the project team did not detect coding errors, missing data or other types of errors in the source data. | Yes No |
| 3.5 | Implementing Solutions – There is an overall risk that changes to procedures would be difficult to implement. This would include additional work on project teams regarding new control procedures. Final Disposition > Based on the four major projects tested, there were no major difficulties with meeting the new requirements. | Yes No |

Section 4. Project Quality

List out major work products / deliverables for this project and indicate what quality control review took place and if the review was approved

| Item | Risk per Project Plan | Reviewer Name | Approved |
| --- | --- | --- | --- |
| 4.1 | Critical to Quality Characteristics / Operating Definitions | John Desanto | Yes No |
| 4.2 | Sampling Plan / Procedures | PMO | Yes No |
| 4.3 | Measurement Systems Analysis | John Desanto and PMO | Yes No |
| 4.4 | Root Cause Analysis | IT Process Board and PMO | Yes No |
| 4.5 | Proposed Solutions | IT Process Board and PMO | Yes No |
| 4.6 | Trend Charts / Control Plans | IT Process Board and PMO | Yes No |

Section 5. Project Costs and Schedule

Using Earned Value Management, what was the final project performance in terms of costs and schedule?

| EMV Parameter | Value | Comments |
| --- | --- | --- |
| Actual Cost | $ 364,000 | As of 2/15/08 – about $ 5,000 more expected |
| Planned Value | $ 480,000 | As of 2/15/08 – where we expected to be |
| Earned Value | $ 510,000 | As of 2/15/08 – where we are at |
| Cost Performance Index | 1.40 | Project required significantly less resources to complete |
| Schedule Performance Index | 1.06 | Solutions were relatively easy to develop and implement |
| Note: The original project schedule was re-baselined in December 2007 when government personnel assigned to the project were released from the project; reduction in scope. |

Section 6.	Resources Deployed and Released

List the resources used during the course of this project and indicate if they have been transferred, reassigned, terminated or planned disposition including effective date.

| Resource | Resource Disposition | Effective Date |
| --- | --- | --- |
| Matt H. Evans – Project Manager | Released to other tasks within the PMO | 3/3/08 |
| Sherry Minzer – Analyst | Released back to OIT Job | 1/11/08 |
| Robert Bowers – Senior Consultant | Released off the Task Order | 2/15/08 |
| Jamin Musului – Senior Analyst | Released back to OIT Job | 1/11/08 |

Section 7.	Project Files

Indicate the location of various artifacts created by this project. This would include all work products, deliverables, minutes, memo’s and all information that would enable someone else to start this project back up with relative ease.

| Work Product / File Name | Location | Point of Contact |
| --- | --- | --- |
| All project files are centrally located on the Network Shared Drive for OIT > PMO > Special Projects > Cost Data Integrity Project | S Drive for OIT > PMO > Special Projects > Cost Data Integrity Project | PMO |

Section 8.	Project Lessons Learned

Identify lessons learned specifically for the project. State the lessons learned in terms of a problem (issue). Describe the problem and include any project documentation references (e.g., Project Plan, Issues Log) that provide additional details. Identify recommended improvements to correct a similar problem in the future.

| Problem or Issue | References | Recommended Changes |
| --- | --- | --- |
| Project came in way under budget – not nearly as complicated as anticipated | EVM Metrics | Re-baseline project and budget earlier and possibly do not force Six Sigma approach when solutions are fairly straight forward. |

Section 9.	Post-Implementation Plans

Identify plans for completing post-implementation activities after project closeout.

| Action | Planned Date | Assigned To | Frequency |
| --- | --- | --- | --- |
| Standard Operating Procedures, Training, and Desk Side Support will be needed for the next seven months. | 3/08 to 9/08 | Program Management Office | As Needed |
| Control Chart Tracking should continue to monitor progress and ensure that all projects comply. | 3/08 to 9/08 | Program Management Office | Monthly |

Section 10.	Open Issues

Describe any open issues and plans for resolution within the context of project closeout.

| Issue | Planned Resolution |
| --- | --- |
| Over 10 different projects have not been included in any real post implementation work as of 2/22/08. | The PMO is charged with making sure all remaining projects become compliant with new control procedures. |