## FMEA
FMEA Report No. 1 - 8/10/07
Process or Product Name: | Integrity of Costs in Monthly Performance Reports (MPR) | [5 empty] | Prepared by: Matt Evans |  |  | Page 1 of 1
Responsible: | Project Management Office (PMO) | [5 empty] | FMEA Date (Orig) 8/10/2007 (Rev) _____________ |  |  |  |  | NOTE: This is the initial FMEA and more robust actions will be taken later in the project life cycle.
Process Step | Key Process Input | Potential Failure Mode | Potential Failure Effects | How Severe to Customer | Potential Causes | Frequency of Error | Current Controls | Current Ability to Detect Error | RPN | Actions Recommended | Resp. | Actions Taken | How Severe to Customer | Frequency of Error | Current Ability to Detect Error | RPN
Submission of Time Sheets | Employees entering Timesheets into Project Management System | Employees fail to enter and submit weekly timesheets for updating the Project Schedule | Project Costs are under-stated in the Monthly Performance Reports and Project Schedules are incorrect in terms of time spent and progress to date | CIO considers this very severe since it impairs the reliability of performance information. RPN Factor = 5 | No program controls or manual check list controls in place for all IT projects. Project Managers are not approving weekly timesheet submissions. | Weekly. RPN Factor = 4 | Project Managers are responsible for making sure that all team members have entered time sheets into the Project Management System. Time Sheet approval screen provides employee listing. | Relatively easy if Project Managers approve time sheets every week. RPN Factor = 2 | 11 | PMO Communication Memo to be issued to all Project Managers with Procedure Paper / Screen Shots attached. Project Team to develop more robust solutions. | PMO | What are the completed actions taken with the recalculated RPN? Be sure to include completion month/year |  |  |  | 0
Submission of Vendor Invoices | Contractor's invoices are received and entered into the Project Management System | Project Cost Analyst does not receive and enter vendor invoices into the Project Management System. | Project Costs are under-stated in the Monthly Performance Reports and Budget Comparisons are off for the respective contract. | CIO considers this very severe since it impairs the reliability of performance information. RPN Factor = 5 | No automatic interface between systems. No reconciliations between systems. Document flows fail to include Cost Analyst. | Monthly. RPN Factor = 3 | Contracting Officers who administer contracts send copies of vendor invoices to Cost Analyst for entering into Project Management System. | Somewhat difficult since Cost Analyst must manually track and monitor each month. RPN Factor = 4 | 12 | Project Team will evaluate current process and develop improvements | PMO |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on J11: Risk Priority Number or RPN. RPN = Severity x Probability x Detection. RPN establishes a priority for each process step. Use a scale of 1 to 5 with 5 as highest and sum each of the three factors.
Cost Data Integrity Project Failure Modes and Effects Analysis (FMEA)