## Table of Contents
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Table of Contents
Tab | Title
1 | System Development Life Cycle (SDLC) | Examples and Overview of Life Cycle Approachs
2 | Different Types of Requirements | Breakdown of different requirement type documents
3 | Stakeholder Analysis | Template for assessing stakeholders
4 | RACI Communication Matrix | Template for communication during requirements work
5 | Business Requirements | Template of critical questions to ask
6 | End User Analysis | Template for assessing end user involvement
7 | Collect Requirements | Template for capturing Stated Requirements
8 | Gap Analysis | Template for highlighting the as is and to be states
9 | Requirements Specification | Specific tips for writing your requirements
10 | Traceability Matrix | Simple template to facilitate traceability
11 | Change Request Form | Simple template for change requests
This workbook is used in conjunction with a course that is subject to copyright protection. You may print, download and use this workbook for your own personal use in conjunction with this course. You may not reproduce or redistribute this workbook without first obtaining the express permission of the author: Matt H. Evans, CPA, CMA, CFM Email: matt@exinfm.com Phone: 1-877-807-8756

## 1 - SDLC
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Quick Overview of System Development Life Cycle (SDLC)
The classic waterfall approach to a life cycle often consists of several important phases and work products |  |  |  | Workbook Menu
as illustrated below. Requirements are often developed early in the System Development Life Cycle (SDLC): |  |  |  | 1 - System Development Life Cycle
2 - Types of Requirements
3 - Stakeholder Analysis
4 - RACI Communication
5 - Business Requirements
6 - End User Analysis
7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
10 - Traceability Matrix
11 - Change Request Form
Two more examples of the Waterfall approach to the System Development Life Cycle:
It is important to define your overall life cycle since your life cycle will often guide
you as to the work you must perform and the work products you must deliver
At the other extreme of the Waterfall is a much more iterative life cycle with much shorter releases:
Spiral SDLC
Under the Spiral approach you still may have many of the same deliverables as under the Waterfall approach:
Concept Definition Work
Project Management Plan
Software Acquisition Plan
Risk Management Plan
Configuration Management Plan
Concept of Operations
Requirements Validation Work
Software Configuration Management Plan (SCMP)
Software Quality Assurance Plan (SQAP)
Software Development Plan (SDP)
Software Unit Testing Plan
Software Coding Standards and Naming Conventions
Database Coding Standards and Naming Conventions
Software Test Plan
Implementation Work
Software Design Description - As Built
Database Design Description - As Built
Software User Documentation
Software Training Manual
Independent Verification and Validation Plan
Project Implementation Plan
Software Maintenance Plan
Iterative Work Products
System Requirements Specification
Software Requirements Specification
Software Design Description
Database Design Description
A popular approach to the Spiral approach is Agile:
Several major features form a program
release and programs are managed at
the Portfolio level
Smaller components eventually roll-up
to major features at the Program level
If you need to learn more, consider purchasing this book!
Source: The Big Picture of Agile Requirements by Dean Leffingwell
Reference Standard for Life Cycles:
IEEE 12207 - Standard for Information Technology - Software Life Cycle Processes
Survey of Life Cycles Used - "Check all techniques or methodologies you currently use, wholly or partially:
Source: Forrester Research, Inc. - December 2008 Global Agile Company Online Survey

## 2 - Req Types
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Different Types of Requirements
Developing requirements typically starts with a definition of scope followed by some type of conceptual |  |  | Workbook Menu
design which leads to lower level requirements. Since you are dealing with a wide range of stakeholders, |  |  | 1 - System Development Life Cycle
from project sponsors at a high level to database developers at a detail coding level, you will have to |  |  | 2 - Types of Requirements
create a set of requirements at different levels. Some examples are summarized below: |  |  | 3 - Stakeholder Analysis
4 - RACI Communication
5 - Business Requirements
6 - End User Analysis
7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
10 - Traceability Matrix
11 - Change Request Form
A. Three Common Requirement Work Products
1 | Concept of Operations - High level conceptual requirements of what must change in terms of
overall capabilities, aligned to one or more business objectives.
2 | User Requirements - What capabilities must be delivered to users to meet their objectives
3 | System Requirements - Capabilities that must be built for the system itself which you can
sub-divide into lower type requirements such as hardware, software, networks, etc.
B. Sub System Types of Requirements
1 | System Architecture - Programming languages, databases, operating system, etc.
2 | Security - Who will have access to databases, hardware, software, etc. How will users be setup
for read, write, and other functions at different levels.
3 | Hardware - Server configuration, network configuration, minimum hardware infrastructure, etc.
4 | Software - What the software will do, what data will it import and export, what types of data will
it process, what functions will the software provide, etc.
5 | Performance - Response and throughput of servers, networks, databases, etc.
6 | Database - Replication, archiving, restoration, and storing of data
7 | Interface - Types of interfaces with system:
Flat Files (slowest) such as ASCII, XML, Binary, etc.
Database-to-Database - Most common interface consisting of tables
Process to Process (fastest) - Instant messaging, TCP/IP, XDR, etc.

## 3 - Stakeholder Analysis
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Stakeholder Analysis
One of the first activities you should conduct for developing requirements is to understand various stakeholders. Stakeholders are people who are |  |  |  |  | Workbook Menu
impacted by your project. They can include customers, different users of the product, sponsors of the project, executive management, etc. Each has a |  |  |  |  | 1 - System Development Life Cycle
different level of interest and a different level of power or influence. You should map each group and its relative interest and influence so you will know |  |  |  |  | 2 - Types of Requirements
how to manage each stakeholder group during the course of the project. |  |  |  |  | 3 - Stakeholder Analysis
4 - RACI Communication
|  | Rate on a Scale 1 (Lowest) to 5 (Highest) |  |  | 5 - Business Requirements
|  | Level of | Level of |  | 6 - End User Analysis
Stakeholder Name | Role & Responsibility | Involvement | Interest | Key Point of Contact | 7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
10 - Traceability Matrix
11 - Change Request Form
Customer - Stakeholder that pays for the project
End User - Stakeholder who directly or indirectly uses the project's product or system
Sponsor - Stakeholder who supports and oversees the project
Champion - Stakeholder who has a vested interest in the successful outcome of the project
Executive Management - Stakeholder who has ultimate authority over the project
Contractor - Third party stakeholder that supports the project directly or indirectly
External Product or System - Products and / or Systems that are impacted by the project
External Entity or Group - Groups outside of the organization that have some interest in the project (such as Vendors, Regulatory Agencies or the General Public)

## 4 - RACI Communication
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Communication Matrix for Requirements Process
You can setup a matrix for how to communicate with different stakeholders using the RACI Matrix
| Project Team |  |  |  |  | Project Support |  |  |  | Stakeholders
| Program/Project Manager | Applications, Enterprise, Technology and Data Architects | Application Developer | Business Analyst | Solution Architect | Enterpise Architect | Design Review Board | Technology Architect | Technology Support | Executive Sponsor | Executive Committee | Program/Project Sponsor | Executive/Program/Project Sponsor | Account Manager/Service Manager | Work Product Reviewer | Key User | Steering Committee
4.1. Analyze Functional Requirements | R
4.1.1 Confirm User Subject Matter Experts for Requirements Definition | R | [8 empty] | I |  | A |  | C | I | I | I
4.1.2 Develop Solution Context Diagram | R |  | C | C | A | C |  | C | [6 empty] | C | C
4.1.3 Develop Process Model | R |  |  | A | [7 empty] | C |  |  | C | C
4.1.4 Develop High-Level Data Model |  |  | A | C | R |  |  | C |  |  |  | C |  |  | C | C
4.1.5 Develop Use Cases | R |  | A | C | C | [6 empty] | C |  |  | C | C
4.2. Analyze Non-Functional Requirements | R
4.2.1. Identify Technology Platform Requirements | R |  |  |  | A |  |  | C | C |  |  | C |  |  |  | I
4.2.2. Evaluate Architecture Requirements | R |  | C | C | A | C |  | C | C |  |  | C |  |  |  | C
4.2.3. Define Reliability, Availability, Service Level Needs | R |  | C | C | A |  |  |  |  | C | [5 empty] | C
4.2.4. Define Performance Needs | R |  | C | C | A |  |  |  |  | C | [5 empty] | C
4.2.5. Identify Security, Legal, Regulatory and Compliance Needs | R |  | C | C | A |  |  |  |  | C | [5 empty] | C
4.2.6. Identify Constraints and Assumptions | R |  |  |  | C |  |  |  |  | A | C | [5 empty] | C
4.3. Conduct Gap Analysis | R
4.3.1. Map As Is and To Be Process | I |  | C | C | RA | C |  | C | C | I |  |  |  | A |  | I
4.3.2. Identify Functional Gaps | R |  |  | C | A | [6 empty] | I |  |  |  | C | I
4.3.3. Develop Strategies to Address Gaps | R |  |  |  | A | C |  | C | C | C | C | C |  | A |  | I | I
4.3.4. Define New Capabilities Needed | R |  |  | C | A | C |  | C | C | C | C | C |  | A
4.4. Specify Requirements | R
4.4.1. Compile Requirements | R |  | A | C | C |  |  |  |  | I | I | I |  | A | C | C
4.4.2. Assess and Rank Requirements | R |  | C | C | A |  |  |  | C | C | C | C |  | A | C | C | C
4.4.3. Group and Phase Requirements for Implementation | R |  | C | C | A |  |  |  | C | C | C | C |  |  | C | C | C
4.4.4. Publish Requirements Specification | R |  | A | I | I |  |  |  |  | I | I | I |  |  | I | I | I
4.5. Obtain Sign-Off of Requirements
4.5.1. Conduct Requirements Review with Sponsors | R |  | A | [7 empty] | C | C |  |  |  | I | C
4.5.2. Address Requirements Review Issues | R |  | A | [8 empty] | I |  |  | I | I
4.5.3. Obtain Sponsor Approval of Requirements | R |  | A | [7 empty] | A | C |  |  | C | I | C
| R | Responsibility: person or role responsible for doing or completing the item
| A | Accountable: person or role accountable for ensuring that the item is completed
| C | Consulted: person or role whose subject matter expertise is required in order to complete the item
| I | Informed: person or role that must be kept informed of the status of item completion
Role
Activity

## 5 - Business Req Review
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Understand Your Business Requirements
A good place to start when comes to understanding requirements is to start at a very high level. We can refer to | Workbook Menu
these as our Business Requirements. This is important since you want to be clear as to the scope of your | 1 - System Development Life Cycle
project and this is rooted in your business requirements. You should try to get answers to these questions: | 2 - Types of Requirements
3 - Stakeholder Analysis
What is the Problem or Business Need? | 4 - RACI Communication
5 - Business Requirements
6 - End User Analysis
7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
What is considered within the Scope of the Project? | 10 - Traceability Matrix
11 - Change Request Form
What is considered outside the scope of the Project?
What are we trying to achieve? (Objectives)
Who is involved? (Stakeholder Analysis)
What Assumptions, Constraints and Risk are involved?
Why are we doing this project? (Justification)
What are the major milestones or events for this project?
What key deliverables or work products will this project produce?
How much commitment exists for this project amongst various stakeholders? (Stakeholder Analysis)

## 6 - End User Analysis
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Categorize Your End Users
People who use your products or systems will have different levels of use. You should categorize different end user |  |  |  | Workbook Menu
groups according to their unique use since this will influence how you prioritize your requirements; i.e. the heavy and |  |  |  | 1 - System Development Life Cycle
intense end users tend to have a higher priority than the casual end user. |  |  |  | 2 - Types of Requirements
3 - Stakeholder Analysis
End User Group | How is the product or system used? | Frequency of Use | Where is it Used? | 4 - RACI Communication
5 - Business Requirements
6 - End User Analysis
7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
10 - Traceability Matrix
11 - Change Request Form
Manager - Works with the product or service for the benefit of someone else
Direct User - Heavy user of the product or service to do their job
Indirect User - Casual use of the product or service to do work as needed
Interface User - Use of another product or service which depends on the subject product or service

## 7 - Collection Template
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Requirements Collection Template
ID | Key Question to Ask | Source Name | Source Location | Elicitation Technique | Analyst | Date | Requirement Description
BR1 | Describe how the user will use the product | John Saxton - Chief Product Engineer | HQ - Hartford, CT | Face to Face Interview | Charles Bradford | 2009-02-17 | Product will be simple to use, only two switches
BR: Business Requirement

## 8 - Gap Analysis
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Gap Analysis
After you have completed requirements elicitation, you will need to compare your requirements with the current | [5 empty] | Workbook Menu
as is environment in order to identify shortcomings with your current capabilities. These shortcomings represent | [5 empty] | 1 - System Development Life Cycle
gaps that you may need to address in order to meet the needs of various stakeholders. | [5 empty] | 2 - Types of Requirements
3 - Stakeholder Analysis
ID | Requirement | Current State | Desired State | Capabilities Needed | Risk if not Met | 4 - RACI Communication
5 - Business Requirements
UR1 | Product needs small light for easier use | Does not exist | Small light at cutting edge of tool | Redesign and manufacture with light | Unable to meet customer expectations | 6 - End User Analysis
7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
10 - Traceability Matrix
11 - Change Request Form
UR: User Requirement

## 9 - Req Specification Tips
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Specific Tips for Requirements Specification
Here are some tips for developing a good set of requirements: |  |  | Workbook Menu
1 - System Development Life Cycle
A. Make sure your requirement is: |  |  | 2 - Types of Requirements
3 - Stakeholder Analysis
| Necessary - Meets a real need that must be met |  | 4 - RACI Communication
| Verifiable - Can be tested somehow (Test Case) |  | 5 - Business Requirements
| Attainable - You can actually build this capability |  | 6 - End User Analysis
| Concise - Single statement that expresses what is needed in terms of a capability |  | 7 - Requirements Collection Template
| Independent - Describes a capability and not a specific solution |  | 8 - Gap Analysis Template
| Unambiguous - Can be interpreted only way by different people |  | 9 - Requirements Specification Tips
| Traceable - Can be traced throughout your documentation using unique identification |  | 10 - Traceability Matrix
11 - Change Request Form
B. Make sure your requirement does NOT:
Consist of multiple sentences
Consist of a table, matrix or other expanded reference
Include nested or multiple conditions
Include adverbs, adjectives, acronyms or abbreviations
C. Structure and Wording:
Use a standard type format that consists of a single statement with the Subject
first followed by the Capability followed by the Condition or Criteria:
The <SUBJECT> shall <CAPABILITY> when the <CONDITION>
| Example | The Financial Reporting System will generate a report of accounts that
are out of balance within 6 hours after the monthly closing date.
Given <CONDITIONS>, the <SYSTEM> shall <BEHAVIOR> where <FACTOR>
| Example | Upon user request, the Trouble Ticket Handling System shall route the submission
to the next available support operator.
The <SUBJECT> shall generate <OUTPUT> if <CONDITION> where <FACTOR>
| Example | The Local Area Network shall generate an alert message if the user's password
expires within 10 days.
Include a key action word such as the following:
Shall - Use when this is a requirement that must be met (most of your requirements should use this word)
Should - Use when this is a recommended requirement that is desireable, but not required.
Will - Use when this is a mandatory practice, procedure or standard (such as a business rule or contract requirement)
D. Examples of Bad Requirements
| Example | The data will need to be classified, easy to maintain, operate, and user friendly with the
Interface Wizard Utility package used by our competitors.
Too many embedded requirements in a single sentence. Not clear as to what each capability
represents (such as user friendly), cannot test the requirement, appears to be unattainable,
and the requirement implies what the solution should be.
| Example | The Business Warehouse shall be able to conduct other forms of analysis.
Very ambiguous - what are other forms of analysis? Cannot test this requirement and
it may not be obtainable unless you are more specific.
| Example | The System shall have the ability to respond to a query request within 20 seconds for
moderate to highly complex related queries.
Ambiguous as to what a moderate to highly complex query is - this makes the
requirement difficult to test and it may be unattainable.
| Example | The System shall provide the capability of browsing data.
Ambiguous as to what browsing data represents - need to be more specific
| Example | The System shall capture inputs in real time from souce systems.
Ambiguous as to what source systems, indicate them by name

## 10 - Traceability Matrix
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Requirements Traceability Matrix (RTM)
You need to identify and cross-reference difference levels in your requirements so that everything maps and aligns | [6 empty] | Workbook Menu
together within the following framework: | [6 empty] | 1 - System Development Life Cycle
2 - Types of Requirements
3 - Stakeholder Analysis
4 - RACI Communication
5 - Business Requirements
6 - End User Analysis
7 - Requirements Collection Template
8 - Gap Analysis Template
9 - Requirements Specification Tips
10 - Traceability Matrix
11 - Change Request Form
Project Name
Project Description
Project Manager
Business Analyst |  |  | < Responsible for maintaining the RTM
Business | Concept of | User | System | Sub System | Test | Design
Requirement | Operations | Requirements | Requirements | Requirements | Case | Documentation
Reference | Reference | Reference | Reference | Reference | Number | Reference

## 11 - Change Request Form
Supplemental Workbook for Module 2 Course 3 - Developing Requirements
Change Request Form
You must establish a change control process to prevent scope creep on a project and to ensure that you process | [6 empty] | Workbook Menu
changes within a framework of Configuration Management. | [6 empty] | 1 - System Development Life Cycle
2 - Types of Requirements
|  | CHANGE REQUEST FORM |  |  |  | Number ____________ | 3 - Stakeholder Analysis
4 - RACI Communication
Requested by | [6 empty] | 5 - Business Requirements
Date Requested | [6 empty] | 6 - End User Analysis
Phone Number | [6 empty] | 7 - Requirements Collection Template
Email Address | [6 empty] | 8 - Gap Analysis Template
Project Name | [6 empty] | 9 - Requirements Specification Tips
10 - Traceability Matrix
Type of Change: | [6 empty] | 11 - Change Request Form
| New Requirement |  | Legal/Marketing |  | Performance Issue
| Bug/Defect/Error |  | Customer Requested |  | Modification/Enhancement
Other ___________________________________________________________________
Priority:
| Critical |  | Important |  | Routine
Configuration Items Involved:
| Software |  | Hardware |  | Documents
Other ___________________________________________________________________
Describe the proposed change:
Has an Impact Assessment been made for this change?
| Yes |  | No |  | In Progress
If Yes to Impact Assessment, list any attachments (such as Cost Estimates, Schedules, etc.)
Describe risks associated with this change
Technical Evaluation:
Reviewed by:
Concurred by:
Impacts to Software/Hardware/Processes:
Impacts to Documentation (Requirements, Test Plans, User Manuals, etc.)
| Requires Change Control Board Approval? |  |  | Yes |  | No
Change Control Board (CCB):
Date Reviewed:
| Action Taken: |  | Approved | Rejected |  | Defer / On Hold
Authorized by:
Explanation: